## Slide 1: Module 3: Session 2
INTRODUCTION TO BUDGETS

## Slide 2: Session Objectives
By the end of the training participants will be able to explain and execute the following:
  To understand the role of a budget in business management
  To relate annual budgets to the business plan
  To budget for depreciation
  To prepare control budgets
  To prepare periodic budgets for contracts

## Slide 3: The role of a budget
A management control and implementation tool
Budgets link spending to plans and activities in a work plan
Monitoring anticipated and actual revenues and costs

## Slide 4: The role of a budget
Monitoring and ensuring that actual spending is in accordance with the budgeted for (planned) expenditures.
Ensuring performance follows activity sequence as in the work plan.
Identifying variances in revenues, expenditures and activity for management attention and correction.

## Slide 5: Relating Budgets and business plan
A business plan is done for a period of several years say 5 and is already a policy statement.
The budget for a period should be done bearing in mind the objectives, targets and strategies that were set in the plan.
A budget is usually done on an annual basis. The budget for a particular year would be done to meet or exceed the targets set in the business plan for that year.

## Slide 6: Guidance to construction budgets
Construction activity is project driven. Therefore, budgeting should be on contract by contract basis.
Since projects have a defined life span, the budgeting cycles will follow the project cycle.
Each project/contract will have a separate operating budget

## Slide 7: Guidance to construction budgets
A construction company has no control over the number of projects it will be awarded in a competitively bid environment.
This is why it is imperative that construction companies adopt project budgeting, i.e. budget as and when a contract is awarded

## Slide 8: The budget process
Start with validating the original tender bid to identify appropriateness and identify any possible need for correction
Contract revenue per period: Break down the contract deliverables and revenues to appropriate periods eg 2kms/month, 0.5kms/week.
Materials and production costs: - derive operational expenses directly associated with contract, gravel, stones, culverts, labour also broken down into corresponding periods as in 2 above.

## Slide 9: The budget process
Administration & Overheads: Estimate indirect expenses such as management payroll, depreciation, marketing, rent, insurance, bad debt and others.
Capital Expenditure: Estimate machinery or automobiles, you plan to use for contract execution, to be hired or purchased.
Interest and Tax : Estimate Interest on loans, taxes such as district levy, and annual licenses.
Cash Flow - Estimate actual cash you will receive and the actual cash payouts that will be made during a certain period including taxes paid, withdrawals, capital items and loan repayments.

## Slide 10: Budgeting for depreciation
Machinery and equipment serve many contracts and a number of years. Their cost is spread as wear and tear over the period of use on contracts.
Provide for a reasonable expected life of the asset by suitable units such as machine hours or mileage.
Spread the cost (less residual value) over the contract based on proportionate budgeted units on the contract or period.
The amount determined as the periodic wear and tear may be used as the budgeted cost of the asset used to earn the revenue.

## Slide 11: Basis for depreciation estimations
Expected life of asset, in machine hours, or time period
Period or units to be used on a contract
Industrial practice rates for depreciation
Previous experience

## Slide 12: Budgets in practice
A budget is a guide and must be flexible to enable the manager to take timely action when needed.
Budget can be revised, when the business environment has radically changed or objectives have changed.
Budgets are flexed to relate to actual output for meaningful control

## Slide 13: Flexing the budget
For cost control management, a cost per basic unit of output can be derived from the budget and used as a yardstick (the standard cost budget).
When units of output are known, the expected cost of actual production is ascertained using the standard cost. This is the flexed budget.
Variances and control action are computed based on the flexed budget rather than the total budget.
For example if we plan to do 24kms of road a year and we do 20kms only, control action is determined by flexing the budget to 20kms first.

## Slide 14: Budget format-labor, materials, machinery
Item of spending | Quantity | Rate | amount
Material | 5,000 tones | 20,000 | 100,000,000
Labor | 2,000 man days | 30,000 | 60,000,000
Machine hire | 100 days | 200,000 | 20,000,000
Total direct cost |  |  | 180,000,000

## Slide 15: Group Activity
Develop a 3 months operations budget for 6kms of the 24kms contract of road that has been awarded to Munaku.
Develop a cash budget for first three months of the contract.

## Slide 16: Q & A
THE END