## Slide 1: Costing and Pricing of Road Works: Building up of rates
Module 6 session five
Notes: DG Notes:
What is the difference between Costing and Pricing? Costing is explained in a slide but Pricing isn't.

## Slide 2: Objectives of the Session
Identify factors to consider during pre-tender site visits and meetings that affect costs of road works
Use works scenarios to build up appropriate activity costs
Determine pricing of contract activities
Practice determination of pricing rates

## Slide 3: Costing Road Works
Involves the accumulation of expenses to determine the likely cost of a contract activity or a unit of output.
The unit of output could be a standard unit like a linear or square metre of road or cubic metre of gravel.
It could be a segment of the contract such as the construction of 500 metres of drainage or an access road to a quarry.
It could be an activity of the contract e.g. Compacting gravel.
Notes: DG Note:
But nowhere in this section does it cover the building up of “Unit Rates” for BoQ activities using Labour, Plant and Material cost component to calculate a m2 rate or linear metre rate etc.

## Slide 4: Why contractors cost road works
To estimate and control resources used in road construction
To determine an appropriate price to charge for works done to:
  Avoid being uncompetitive
  Avoid undercharging
To compare costs and profitability of different road contracts, components or sections.
To benchmark with competitors.
Notes: DG Note:
This is an oddly phrased question and slide? Needs clarification as to what this slide actually means and what it is trying to say? Is it trying to ask why it is important for a contractor to properly cost/price his work using labour, plant and material inputs.?

## Slide 5: Approach to costing works
A contractor may build up costs of works activities using the zero based budgeting approach for each assignment.
From past experience a contractor may have built up costs for common activities that may still be relevant
A contractor may also use costs established by entities such as MoWT /FIDIC and adjust them to suit their circumstances.
Whatever approach used the costs should be reviewed after visiting the site of the works, assessing competition and examination of the project plans to suit the circumstances.
Notes: DG Notes:
What does this mean? What are standard costs? Does it mean "standard BOQ items or activities? David 25/09/2013
I am not familiar with the expression “zero budget/cost approach”. What does it mean?
Why is the Contractor expected to develop his own BOQ?. The BoQ is prepared by the Consultant and provided to the Contractor as part of the tender documents. If not the is the Contractor expected to submit a Lump Sum bid? If so that will change his approach to pricing/costing the works.

## Slide 6: What to watch out for on a pre-bid site visit
The terrain
The nature of soils and vegetation
Source of major raw materials, hardware
Availability of basic amenities for staff such as:
  Accommodation, food and water
Source and cost of labour
Security of person and assets
Each of these would in one way or another affect the cost of works.

## Slide 7: Components of road works costs
Direct costs are those necessarily incurred for the road works
  Labour, materials and direct expenses.
  Equipment hire or depreciation charge.
  Consumables.
  Mobilization and demobilization
Indirect costs (overheads) e.g.
  Costs of head office
  Administrative expenses
  Management emoluments
  Data processing
  A suitable absorption rate may be used to cater for indirect costs.

## Slide 8: Common components of gravel roads costs (level1)
Site preparatory costs
Setting out and site clearing costs
Earth works costs
Drainage works
Gravelling and completion
Preliminary and generals items
To determine costs, break down the components into simple measurable lower level activities.

## Slide 9: Site preparatory works – lower level activities
Establishment of camps and their maintenance
Construction of access road to quarry sites and its maintenance:
  Construction of access roads
  Maintenance of access roads
Construction of diversions and their maintenance
  Construction of diversions
  Maintenance of diversions
These are costs essential to administer, access materials for road construction and to also allow traffic to flow during works (traffic count).

## Slide 10: Site preparatory works – lower level activities
Construction of access road to quarry sites consists of the following operations that are costed:
    Mobilization
    Machine hire and fuel
    Machine operators
    Technicians
    Overheads
    Costs are built up from the lowest level activity then carried to the higher level activity for bidding

## Slide 11: Site preparatory works – lower level activities
The maintenance of the access road consist of the following activities that are costed:
  Scarifying
  Compaction
  Watering
  These are also broken down to machine hire, fuel, machine operation and overheads then costed.

## Slide 12: Building up costs – Example of construction of the access road
Construction of access roads to quarry sites |  |  |  | 
One kms from site (LS) | Quantity | Cost/unit | Total Cost (shs) | 
(De)Mobilization | 1 |  | 2,000,000 | 
Grader hire (days) | 1 | 1,000,000 | 1,000,000 | 
Fuel | 50 | 3,300 | 165,000 | 
Machine operator | 1 | 100,000 | 100,000 | 
Technician | 1 | 50,000 | 50,000 | 
Admnistrative overhead |  | 7.5% | 238,500 | 
Cost per kms |  |  | 3,563,625 | 
Margin 30% | 1 | 3,563,625 | 1,069,088 | 
Rate per kms |  |  | 4,632,713 | 

## Slide 13: Building up costs: Example of maintenance of the access roads
Access road maintenance (Seven days) |  |  | 
Scarifying (3 times) |  |  | 
Grader hire (days) | 3 | 1,000,000 | 3,000,000
Fuel | 150 | 3,300 | 495,000
Operator | 3 | 100,000 | 300,000
Admnistrative overhead |  | 7.5% | 284,625
Cost |  |  | 3,795,000
Compaction (3 times) |  |  | 
Compactor hire(days) | 3 | 500,000 | 1,500,000
Fuel | 120 | 3,300 | 396,000
Operator | 3 | 100,000 | 300,000
Admnistrative overhead |  | 7.5% | 164,700
Cost |  |  | 2,360,700
Watering ( 3 times a day) |  |  | 
Water bowser | 7 | 500,000 | 3,500,000
Fuel | 140 | 3,300 | 462,000
Operator | 7 | 100,000 | 700,000
Administrative overheads |  | 7.5% | 349,650
Cost |  |  | 5,011,650

## Slide 14: Earth Works Activity
Rehabilitation of existing formation include:
  Reshaping of existing road formation, watering and compaction.
  Opening of chocked culverts
  Opening or re-excavation of side drains
2. Construction of road formation include:
  Excavation to level
  Excavation in side, mitre, catch water and other specified drains
  Form, water and compact road bed.

## Slide 15: Earth Works Activity
3. Provision of fill materials:
  Preparation of Quarry Site consisting of clearing vegetation and removing topsoil
  Excavation, hauling, placing, watering and compaction of approved fill material to create a level road bench.
  Excavation of rock

## Slide 16: Example of Costing and Rate determination: Rehabilitation of existing road formation
3.1.1 Reshaping of the existing road formation including watering and compaction |  |  | 
One km | Quantity | unit cost | Cost
(De)Mobilisation | - | 2,000,000 | -
Grader Hire | 1 | 1,000,000 | 1,000,000
Fuel | 50 | 3,300 | 165,000
Operator (md) | 1 | 100,000 | 100,000
Site Engineer (md) | 1 | 500,000 | 500,000
Surveyor (md) | 1 | 550,000 | 550,000
Lab Technician (md) | 1 | 100,000 | 100,000
Technician (md) | 1 | 100,000 | 100,000
Administrative overheads |  | 7.5% | 188,625
Cost per kms |  |  | 2,703,625
Margin | 30% | 2,703,625 | 811,088
Rate per km |  |  | 3,514,713

## Slide 17: Example of Costing and Rate determination: Removal of chocked culverts
3.1.2 (a) Removal of choked culverts |  |  | 
(De)Mobilisation (backhoe) | 1 | 2,000,000 | 2,000,000
Backhoe hire /day | 1 | 800,000 | 800,000
Fuel | 30 | 3,300 | 99,000
Operator(md) | 1 | 100,000 | 100,000
Site Engineer (md) | 1 | 500,000 | 500,000
Surveyor (md) | 1 | 550,000 | 550,000
Lab Technician (md) | 1 | 100,000 | 100,000
Technician (md) | 1 | 100,000 | 100,000
Administrative overheads |  | 7.5% | 318,675
Cost/kms |  |  | 4,249,000
Margin | 30% | 4,249,000 | 1,274,700
Rate (price) per kms |  |  | 5,523,700

## Slide 18: Example of Costing and Rate determination: Opening of drains
b) Opening / re-excavation of side, mitre, catch water and other spec. drains | Units | Unit cost | 
Backhoe hire | 1 | 800,000 | 800,000
Fuel | 30 | 3,300 | 99,000
Operator | 1 | 100,000 | 100,000
Site Engineer (md) | 1 | 500,000 | 500,000
Surveyor (md) | 1 | 550,000 | 550,000
Technician (md) | 1 | 100,000 | 100,000
Administrative overheads |  | 7.5% | 161,175
Cost per kms |  |  | 2,149,000
Margin | 30% | 2,149,000 | 644,700
Rate per kms |  |  | 2,793,700

## Slide 19: Example of summary costing and Pricing: Rehabilitation of existing road formation
Summary of three activities | Unit | Quantity | Cost | Margin | Rate ( price)
Reshaping of existing road | Km | 1 | 2,703,625 | 811,088 | 3,514,713
Removal of choked culverts | Km | 1 | 4,249,000 | 1,274,700 | 5,523,700
Opening/re-excavation of drains | Km | 1 | 2,149,000 | 644,700 | 2,793,700
Total Rehabilitation of existing road. | Km | 1 | 9,101,623 | 2,730,488 | 11,832,113

## Slide 20: Example of labour based costing and pricing rates
Activity | Unit | Expected Daily Task Range | Rate per day (shs) | Cost per unit (shs) | Margin | Pricing rate
Setting out | METRE | 100 | 24,000 | 240 | 50% | 360
Bush clearing – light | SQUARE METRE | 350 | 15,000 | 43 | 50% | 64
Bush clearing - medium | SQUARE METRE | 200 | 15,000 | 75 | 50% | 113
Bush clearing – heavy | SQUARE METRE | 100 | 15,000 | 150 | 50% | 225
Stripping and grubbing | CUBIC METRE | 175 | 15,000 | 86 | 50% | 129
Tree cutting No. - | EACH | 5 | 15,000 | 3,000 | 50% | 4,500
Stump removal No. - | EACH | 2 | 15,000 | 7,500 | 50% | 11,250
Boulder removal - Day work |  | 3 | 15,000 | 5,000 | 50% | 7,500
Excavate ordinary soft soil | CUBIC METRE | 5 | 15,000 | 3,000 | 50% | 4,500
Excavate ordinary medium soil | CUBIC METRE | 3.5 | 15,000 | 4,286 | 50% | 6,429
Excavate hard soil | CUBIC METRE | 3 | 15,000 | 5,000 | 50% | 7,500
Excavate very hard soil | CUBIC METRE | 2 | 15,000 | 7,500 | 50% | 11,250
Excavate rock | CUBIC METRE | 0.8 | 15,000 | 18,750 | 50% | 28,125
The expected daily task range is per MoWT Vol2 Man A2. |  |  |  |  |  | 

## Slide 21: Preliminary and General Items
Mobilisation and Demobilisation
Insurances and Bonds
Traffic Accommodation
Bill Boards
Maintenance of the whole of the Works
Supervision of the Project by the Employer
Site meetings and with local communities
Allow for sign posts
PROVISIONAL 5% FOR CONTINGENCIES

## Slide 22: Example of staff Cost and Price rates
 | Unit | Cost/hr | Margin -50% | Rate/hr | Cost /day | Rate per day
Unskilled labour | hr | 2,500 | 1,250 | 3,750 | 20,000 | 30,000
Skilled labour | hr | 3,000 | 1,500 | 4,500 | 24,000 | 36,000
Headman | hr | 4,000 | 2,000 | 6,000 | 32,000 | 48,000
Foreman | hr | 5,000 | 2,500 | 7,500 | 40,000 | 60,000
Engineer | hr | 10,000 | 5,000 | 15,000 | 80,000 | 120,000
Site Manager | hr | 15,000 | 7,500 | 22,500 | 120,000 | 180,000
Driver heavy | hr | 3,500 | 1,750 | 5,250 | 28,000 | 42,000
Driver Light | hr | 3,000 | 1,500 | 4,500 | 24,000 | 36,000
Plant operator H/D | hr | 5,000 | 2,500 | 7,500 | 40,000 | 60,000
Plant operatorLH/D | hr | 4,000 | 2,000 | 6,000 | 32,000 | 48,000
Land surveyor | hr | 5,000 | 2,500 | 7,500 | 40,000 | 60,000
Draftsman | hr | 4,000 | 2,000 | 6,000 | 32,000 | 48,000

## Slide 23: Example of Equipment costs and pricing rates
Equipment | Unit | Cost/hour | Rate/hr (C+25%) | Rate per day
D4 Dozer or equivalent with blade and ripper | hr | 35,000 | 43,750.00 | 350,000.00
D8 Dozer or equivalent with blade and ripper | hr | 40,000 | 50,000.00 | 400,000.00
Wheeled excavator, bucket capacity under 1 m3 | hr | 58,000 | 72,500.00 | 580,000.00
Track Loader, 3-4 m3 backet capacity, (Cat 973C or equivalent) | hr | 100,000 | 125,000.00 | 1,000,000.00
Wheeled excavator, bucket capacity 1-2 m3 | hr | 33,000 | 41,250.00 | 330,000.00
Backhoe loader | hr | 58,000 | 72,500.00 | 580,000.00
5t tipper lorry | hr | 28,000 | 35,000.00 | 280,000.00
9t tipper lorry | hr | 35,000 | 43,750.00 | 350,000.00
Dump Truck | hr | 30,000 | 37,500.00 | 300,000.00
Motorgrader, complete with scarifier (Cat. 14 or equivalent) | hr | 45,000 | 56,250.00 | 450,000.00

## Slide 24: Group Activity
All groups:
Practice building up cost and price rates for key staffs
Practice to build up costs and price rates for Magege gravel and completion works.
What are the difficulties experienced?
Notes: DG Note:
Yet again I question whether this is practical or required, especially given the limited time available? Probably not in my opinion.