## Slide 1: Management of Contracts (1) Module Six: Session 8

## Slide 2: Objectives
Outline the roles and responsibilities of the different stakeholders in contract management
Discuss risks faced by contractors during management of contracts
Discuss mitigation measures for contract risks
Share contract management experiences

## Slide 3: Overview of Contract Management
Contractors sign contracts after winning tenders
Contracts are legally and commercially binding documents that direct how the road contract will be implemented
A contract is managed within the time period of the road project being implemented
Contract management is the process of ensuring that the contractor’s performance meets contractual requirements

## Slide 4: Consequences of poor contract management
Decisions are delayed or not taken
Loss of time, cost overruns and financial loss
Straining of employer-contractor relationship may result
Substandard work may result with a risk of losing reputation and getting blacklisted.
Contract staff fail to understand their obligations and responsibilities
There are misunderstandings, disagreements and underestimations; too many issues are escalated inappropriately;
Environmental degradation and accidents

## Slide 5: Reasons why organizations fail to manage contracts successfully
Failure to read and interpret the contract designs and documents
Inadequate resources assigned to the contract management;
The wrong people put in place;
Authorities or responsibilities relating to commercial decisions of the contract are not clear;
Lack of monitoring and performance measurement;
Failure to identify and mitigate risk.

## Slide 6: Importance of a signed Contract
Is the focus of contract management
Forms a permanent point of reference
Sets out clear specifications, obligations and expectations of both parties
Anticipates and handles disputes as they arise within and after the contract period
Ensures compensation for the deliverables is known and honoured.

## Slide 7: Common contractual content
Performance Security
Advance Payment
Quality test plan/QTP/ITP
Schedule of work
Request for Approval
Request for Inspection
Variation Orders
Site Diary
Weather Record
Interim Certificates
Snag list
Site meetings
Defects liability
Retention
Certificate of substantial completion
Certificate of final completion
Final Payment Certificate
Release of retention
Liquidated damages

## Slide 8: Triple Constraint of Contract Management
Cost
Schedule/Time
Performance
Contractors should aim at managing the triple constraint through out the contract

## Slide 9: Tools of Contract Management
The contract
The time schedule
Project management plan (PMP)
Cost Plan
Specifications
Notes: DG Notes:
Added two bullet points re. Cost Plan and Specification

## Slide 10: Activity Scheduling
Breakdown the activities to small and measurable units- (Work Breakdown Structures (WBS))
Activity | Jan | Feb. | Mar | Apr | May | June | July | Aug | Sep
Mobilization & Site Clearing | **** | **** |  |  |  |  |  |  | 
Earth Works |  |  | *** | *** |  |  |  |  | 
Drainage works |  |  |  |  | *** | *** |  |  | 
Gravelling and completion |  |  |  |  |  |  | *** | *** | 
Preliminary and generals items | **** | *** | *** | *** | *** | *** | *** | *** | ***

## Slide 11: The project management plan (PMP)
PMP includes a series of actions, resources, changes or operations that bring out an end result in management of a road contract.
PMP is aimed at ensuring that a contractor manages cost, schedule and technical performance.
PMP ensures that the contracts Key Result Areas (KRAs) are achieved.

## Slide 12: Focus of PMP
Planning-Identification of works structure and appointment of right staff
Evaluation-Assessment of performance at critical stages of the contract
Budget-Execution of contract activities within the budget and financial constraint
Reporting and communication-of successes and failures at critical stages of the contract
Schedule-Contract schedule and timing of critical contract outputs

## Slide 13: Focus of PMP
Stakeholder Management- satisfaction of the stakeholders at different fronts
Financial management- accountability, profit management, internal and external audits
Quality control-execute work within the acceptable standards as indicated in the BOQs and quality specifications
Risk management – identification, assessment and mitigation

## Slide 14: Structure of PMP
Item | Key Result Areas (KRAs)-OVIs | Means of Verification | Assumptions
Planning | Preparation and review of contract plans | Plans in place | Daily progress review
Evaluation | Daily works done | Measurement | Every end of day
Budget | 38m per km | Activity expenditure variance | Activity based budget
Reporting and Communication |  |  | 
Schedule/time |  |  | 
Stakeholders |  |  | 
Cashflow and profitability |  |  | 
Quality Control |  |  | 

## Slide 15: Stakeholders in Contract Management
Any internal or external persons, Institutions that affect the outcome of a contract e.g.
Organizational staff,
Client (LG, UNRA, MoWT)
Supplier/Contractors
Funders
Banks and insurance companies
Public (Road Users)
Civil Society Organizations and Unions
Politicians
NEMA

## Slide 16: Main tasks of a Contract Manager
Reads and analyzes the contract properly
Evaluates organization’s ability to comply with contract conditions
Functions as focal point for internal support/team-members
Protects the financial interests of the organization
Obtains commitments from subcontractors (if any)
Establishes a contract administration plan
Plans and conducts a pre performance conference
Monitors, measures and reports progress

## Slide 17: Roles of a Contract Manager
Manages contract changes
Resolves disputes and ensures timely delivery
Manages the invoice and collection process
Documents decisions and events
Should know who does what, when, where, and why, and how it is documented
Should ensure that everything contractually required is done by appropriate members of the team
Notes: DG Note:
a Contract Manager cannot generally terminate the Conract

## Slide 18: Contract Management Team
A Successful Team:
Has effective communication
Clear Objectives
Defined Roles and Responsibilities
Defined project expectations
Accountability of all team members
Dedication from contract management team
Notes: DG Note:
Two items added - Clear Objectives and Defined Roles and Responsibilities.

## Slide 19: Developing a Contract Administration Plan
List key terms & conditions
  identify supplier actions and customer actions
Identify contract milestones, reports & due dates
Identify customer interfaces
Coordinate with Project Manager(PM) for internal effort:
  assign responsibilities
  develop a contract schedule

## Slide 20: Risks in Contract Management
A risk is something that may happen and if it does, will have a positive or negative impact on the contract. Potential areas of risks in contracts Include:
Risk of inaccurate description of the item of works through specifications and legal documents.
Risk of loss of financial and legal interest
Contractual risks - establishing change order procedures
Ground Conditions
Weather
Notes: DG Notes:
Added Ground and Weather Conditions

## Slide 21: Risks Contd.
Risk of failing to complete works timely
  Inadequate monitoring
  Machine breakdown
  Industrial action
  Delayed payments
Performance risks of sub standard work
Price risks – Inflation risk
Financial & Profitability; Risk of non payment
Risk of loss of key staff
Human Behavior Risks – pilferage
Notes: DG Note:
Failing to complete the works in a timely manner is a consequence of other Risks. It is not itself the actual risk.
The question is "What Risks will jeopardise timely completion"?

## Slide 22: Management and Mitigation of Risks
The role of the contract manager is to reduce the level of risk by:
  Understand the elements that constitute risk in projects
  Identify typical risk categories and types of risk in each category and adopt risk management strategies (TARA approach)
  Prioritize risk for probability and consequences of risk
  Evaluate the use of risk mitigation strategies

## Slide 23: Effective Risk Management
23
ASSESS
CONTROL
ANALYSE RISKS
IDENTIFY UNCERTAINTIES
MEASURE & CONTROL
PLAN FOR EMERGENCIES
MITIGATE RISKS
PRIORITIZE RISKS

## Slide 24: Group Activity
Justify the need for contracts management and share experience as to why contractors may fail to successfully execute contracts.
Using the Magege works case and your experience identify the major risks in a road works contract and suggest strategies to deal with them.
Explain what a Project Management Plan is and state What are its major components and focus.
Notes: DG Note:
A general Group Discussion for 15 to 20 minutes on these topics would be more appropriate at this stage.