## Slide 1: Management of Contracts (2) Module Six: Session 9

## Slide 2: Objectives
Identify the different types of resources available to a road contractor
Identify skills of managing different resource on a contract
Create awareness of environmental; Occupational Health and Safety challenges in road construction
Conduct trainee assessment and obtain trainee module evaluation.

## Slide 3: Key resources used in a contract
Time
Skills and labour:
  Management, Technical and Labour
Physical resources
  Materials, Consumables and Equipment
Financial resources to finance the above
These resources must be well utilised to ensure timely, quality and profitable delivery of the contract.
Notes: DG Note:
This slide and this following should come earlier in the presentation – to follow slide 19.

## Slide 4: Contract time management
Activities in a project are identified and their durations and sequencing identified.
Timing of such activity is presented on a GANTT chart
Using a net work diagram critical path activities are identified
Critical path activities are ones without any slack time where any delay on their execution will similarly increase the project time
A project manager must ensure that works follow the scheduled program and that critical path activities are not delayed in any way

## Slide 5: Skills and labour resources
Retain management skills capable of planning and supervising an ongoing contract
Engage staff with appropriate technical skills and experience, able to read and interpret drawings and BOQs.
Some technical staff may be contracted only for periods where the contract requires them
Engage non skilled staff as per demand. These may be on part time or piece rate basis only. Avoid keeping idle staff.
Sub contract where necessary

## Slide 6: Management of equipment and inventory
Keep own equipment securely
Provide routine maintenance to equipment when due
Avoid keeping equipment idle. Could be better to hire equipment not ordinarily utilised
An efficient procurement and stores system should be maintained to manage materials procurement and utilisation
Maintain sufficient internal controls over the inventory of materials and consumables

## Slide 7: Financial Resources
Management of finances is critical to success of the contract.
Plan for adequate finances to meet capital needs, working capital and standby needs
Plan and control costs within activity budgets
Ensure timely work measurements and certification
Follow up and ensure timely payments for certified works
Monitor regularly cash availability and demands

## Slide 8: Environmental Issues
Government is emphasizing good environmental practices. Environmental responsibility issues in road construction include:
Minimizing Carbon & Gas emissions
Avoiding environmental degradation and sustainable resources use:
  grass and tree re-planting,
  Recycling
  Avoidance of pollution
  Restoration of borrow pits
  Erosion control

## Slide 9: Contracts Health and Safety
Organizations must provide a safe working environment for the employees to keep them safe and healthy physically, mentally and psychologically
Provisions of occupational health and safety are prescribed in the law; The Occupational Health and Safety Act 2007.
Organizations must insure against costs of compensation for work related accidents as defined in the Workers Compensation Act 2006.
There is also the public safety concerns under common law.

## Slide 10: Responsibility of Government on OH&S
Enforcement of occupational health and safety legislation. (2007)
Workplace inspections
Registration of occupational incidents and accidents
Dissemination of relevant information
Enforcement of Workers Compensation Act
Promotion of training, education and research
Resolution of OH&S disputes.

## Slide 11: Organization's responsibilities on OH&S
Take every reasonable precaution to ensure the workplace is safe and healthy.
Establish and maintain a joint health and safety committee
Train employees about any potential hazards and how to safely use gadgets and dispose of hazardous substances
Train staff on how to handle emergencies.
Supply free protective gear and ensure workers know how to use them.
Offer voluntary HIV aids sensitisation and protection

## Slide 12: What are the company's responsibilities on OH&S?
Indicate and enclose dangerous areas, gadgets and items
Immediately report all critical injuries to the labour officer responsible for OH&S.
Appoint a competent supervisor who sets the standards for observation of safe working conditions.
Provide appropriate social amenities such as washrooms, drinking water, breaks etc.
Be responsive to gender issues

## Slide 13: Road Site OH&S
Road signage
Protective wear (safety shoes/boots, overalls, masks, helmets, gloves, Reflector jackets )
Traffic controllers
Speed controls
Diversions for waters and carriage
Appropriate communication gadgets
Seal-off tapes
Site clinics (active doctor & nurse)

## Slide 14: What are the employees’ responsibilities on OH&S
Responsibility to work in compliance with OH&S acts and regulations.
Responsibility to use personal protective gear, equipment and clothing provided as directed by the employer.
Responsibility to report workplace hazards and dangers
Responsibility to maintain safety installations
Right to refuse to work if the work environment is perceived to be unsafe

## Slide 15: Record Keeping and Reporting
Establish a suitable contract record keeping system to contain:
Copy of specifications and instructions from employer.
Copies of delivery schedules
Copies of delivery certification.
Documents of any negotiations
Site meeting notes
Reports
Email messages and other communication
Contract management reports.

## Slide 16: Variations in Road Works
A contract variation or change order is a change to the price, completion date or statement of requirements of a contract, which is provided for in the contract to facilitate adaptations to unanticipated events or changes in requirements.
A contract variation may be issued with the approval of the contracts committee and communicated in writing to the contractor.
Any additional funding required for a variation or change order should first be committed.
A single variation should not exceed 15% of the contract price -PPDA guidelines (2003) and MoWT
Notes: DG Note:
Is the 15% figure standard for Ugandan Contracts?

## Slide 17: Contract Variations
A variation or change order should be in accordance with the terms and conditions of a contract and should be authorized by a competent officer.
A contract which provides for a variation or change order shall include a limit on a variation or change order which should not be exceeded without a contract amendment.
Contract variations should not cumulatively exceed 25% of the original contract-PPDA guidelines (2003) and MoWT
Notes: DG Note:
Where is the 25% figure specified?

## Slide 18: Invoicing, Certification and Payments
The contractor should know clearly when certification should be sought for
Certification should be immediately followed by invoicing in accordance with the terms of the contract
A rapport should exist between the contractor, consultants and the employer to facilitates prompt certification and payment
The contractor should consider a cost benefit analysis of stopping work in case of payment default

## Slide 19: Contract Cash flow
Do a cash flow for the project and update it as the contract progresses
Costs and revenues are anticipated and allocated to when they expect to arise. This would indicate any possible cash constraints or excess cash
Plan in advance how to deal with the emerging patterns
Monitor both the payments and the receipts to ensure that there is a smooth cash flow

## Slide 20: Contract Termination
Contract termination happens when parties fail to agree or stick to the contract deliverables or other contract fundamentals
The contract may stipulate the events under which either party may terminate the contract
The client or the contractor may, without prejudice to any other remedy for breach of contract, by written notice of default to the other, terminate the contract in whole or part;
Termination of a contract may involve heavy financial losses, lengthy law suits and could lead to loss of reputation; it should be taken cautiously as last resort.

## Slide 21: Contract- Closeout
Entails completion and settlement of the contract including resolving of any open items
Involves both works verification and administrative closure:
  Updating of records to reflect final results and archiving of such information for future use.
  Was all work completed correctly and satisfactorily?
  Commission and Demobilization
  Lessons learnt
Notes: DG Note:
This should be the final slide of this session.

## Slide 22: Group Activity
Identify the major resources used in a contract and give brief outline how they can be managed
State the major players in the occupation health and safety framework and outline their roles and responsibility.
Administer training evaluation
Conduct trainee Assessment (test)
Wrap up
Notes: DG Note:
A general Group Discussion for 15 to 20 minutes on these topics would be more appropriate at this stage.