## Impact of taxation (hidden)
Ideal (ZBB) bid
Item | cost per unit | Quantity | Cost
Materials: murram in tonnes | 5000 | 20000 | 100000000
Machine hire in hours | 400 | 200000 | 80000000
Fuel for machines in lts | 40000 | 3000 | 120000000
Direct labour (man days) | 900 | 10000 | 9000000
Supervision (man months) | 4 | 500000 | 2000000
Total cost |  |  | 311000000
Margin 30% |  |  | 93300000
Bid price |  |  | 404300000
Impact of Taxation
District levy tax 2% |  |  | 8086000
Expected Corporate Taxation 30% |  |  | 27990000
Net profit |  |  | 57224000
|  |  | 61.3333 | %ge of original
Actual profitability margin |  |  | 18.4

## Model incomes statements (hidden)
Particulars |  |  |  | Munaku project 12 months income statement (shs'000)
Cost item | Narrative |  |  | Jan | Feb | Mar | April | May | June | july | Aug | Sept | oct | Nov | Dec | Total
Kilometres done |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24
Kilometres billed |  |  |  | Munaku project 12 months income statement (shs'000) Feb: 4; Munaku project 12 months income statement (shs'000) April: 4; Munaku project 12 months income statement (shs'000) June: 4; Munaku project 12 months income statement (shs'000) Aug: 4; Munaku project 12 months income statement (shs'000) oct: 4; Munaku project 12 months income statement (shs'000) Dec: 4 | 24
Price per km |  |  |  | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 5400000
Revenue |  |  |  | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 10800000
0
Costs |  |  |  | Munaku project 12 months income statement (shs'000) Sept: statements | 0
Material | 8,000 tonnesx20000 plus vat at 20% |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Direct labour | 60m/kms |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Machine hire | 15m/kms | 12+3=15/kms |  | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 360000
Fuel | 9000ltsx3500 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Overheads | 100m/kms |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Management salaries | 15m/month |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Depreciation | 354,167 per kms | 354.1667 |  | 708.334 | 708.334 | 708.334 | 708.334 | 708.334 | 708.334 | 708.334 | 708.334 | 708.334 | 708.334 | 708.334 | 708.334 | 8500.008
Amortisation | 1,250,000 per kms (for 3 years) |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Interest |  |  |  | 10900 | 10900 | 10900 | 10900 | 10900 | 10900 | 10900 | 10900 | 10900 | 10900 | 10900 | 10900 | 130800
Total cost |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Net profit |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Provision for taxation 30% |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Profit after Taxation |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Return on Investment (assume equity 3.6b) | profit after tax/Equity | #REF!
means could change
shs'000
|  |  |  | Loan amount |  |  | 750000
|  |  |  | Repayment over 48 months- monthly instalment |  |  | 16000 | [5 empty] | 192
|  |  |  | Simple interest calculation |  | Year | Start | Repayed | End | Interest/year per y | Interest/month
[6 empty] | y1 | 750000 | 192000 | 558000 | 130800 | 10900
[6 empty] | y2 | 558000 | 192000 | 366000 | 92400 | 7700
[6 empty] | y3 | 366000 | 192000 | 174000 | 54000 | 4500
[6 empty] | y4 | 174000 | 174000 | 0 | 17400 | 1450
[6 empty] | y5 | 0 | 0 | 0 | 0 | 0
[8 empty] | 750000 |  | 294600 | 24550
Munaku income and expenditure Projections
Year |  | one | Two | Munaku project 12 months income statement (shs'000) Jan: Three; Munaku project 12 months income statement (shs'000) Feb: Four; Munaku project 12 months income statement (shs'000) Mar: Five; Munaku project 12 months income statement (shs'000) April: Total
Road work done in Kms | 0 | 24 | 24 | Munaku project 12 months income statement (shs'000) Jan: 24; Munaku project 12 months income statement (shs'000) Feb: 24; Munaku project 12 months income statement (shs'000) Mar: 24; Munaku project 12 months income statement (shs'000) April: 120
Price offered | Munaku | 450000 | 450000 | Munaku project 12 months income statement (shs'000) Jan: 450000; Munaku project 12 months income statement (shs'000) Feb: 450000; Munaku project 12 months income statement (shs'000) Mar: 450000; Munaku project 12 months income statement (shs'000) April: 2250000
Revenue receipt |  | 10800000 | 10800000 | Munaku project 12 months income statement (shs'000) Jan: 10800000; Munaku project 12 months income statement (shs'000) Feb: 10800000; Munaku project 12 months income statement (shs'000) Mar: 10800000; Munaku project 12 months income statement (shs'000) April: 54000000
Costs
Material | 8,000 tonnesx20000 plus vat at 20% | 4608000 | 4608000 | Munaku project 12 months income statement (shs'000) Jan: 4608000; Munaku project 12 months income statement (shs'000) Feb: 4608000; Munaku project 12 months income statement (shs'000) Mar: 4608000; Munaku project 12 months income statement (shs'000) April: 23040000
Direct labour | 60m/kms | 1440000 | 1440000 | Munaku project 12 months income statement (shs'000) Jan: 1440000; Munaku project 12 months income statement (shs'000) Feb: 1440000; Munaku project 12 months income statement (shs'000) Mar: 1440000; Munaku project 12 months income statement (shs'000) April: 7200000
Machine hire | 15m/kms | 360000 | 360000 | Munaku project 12 months income statement (shs'000) Jan: 360000; Munaku project 12 months income statement (shs'000) Feb: 360000; Munaku project 12 months income statement (shs'000) Mar: 360000; Munaku project 12 months income statement (shs'000) April: 1800000
Fuel | 9000ltsx3500 | 756000 | 756000 | Munaku project 12 months income statement (shs'000) Jan: 756000; Munaku project 12 months income statement (shs'000) Feb: 756000; Munaku project 12 months income statement (shs'000) Mar: 756000; Munaku project 12 months income statement (shs'000) April: 3780000
Overheads | 100m/kms | 2400000 | 2400000 | Munaku project 12 months income statement (shs'000) Jan: 2400000; Munaku project 12 months income statement (shs'000) Feb: 2400000; Munaku project 12 months income statement (shs'000) Mar: 2400000; Munaku project 12 months income statement (shs'000) April: 12000000
Management salaries | 15m/month | 180000 | 180000 | Munaku project 12 months income statement (shs'000) Jan: 180000; Munaku project 12 months income statement (shs'000) Feb: 180000; Munaku project 12 months income statement (shs'000) Mar: 180000; Munaku project 12 months income statement (shs'000) April: 900000
Depreciation | 354,1667 per kms | 8500.008 | 8500.008 | Munaku project 12 months income statement (shs'000) Jan: 8500.008; Munaku project 12 months income statement (shs'000) Feb: 8500.008; Munaku project 12 months income statement (shs'000) Mar: 8500.008; Munaku project 12 months income statement (shs'000) April: 42500.04
Amortisation | 1,250,000 per kms (for 3 years) | 30000 | 30000 | Munaku project 12 months income statement (shs'000) Jan: 30000; Munaku project 12 months income statement (shs'000) Feb: 0; Munaku project 12 months income statement (shs'000) Mar: 0; Munaku project 12 months income statement (shs'000) April: 90000
Interest |  | 130800 | 92400 | Munaku project 12 months income statement (shs'000) Jan: 54000; Munaku project 12 months income statement (shs'000) Feb: 17400; Munaku project 12 months income statement (shs'000) Mar: 0; Munaku project 12 months income statement (shs'000) April: 294600
Total cost |  | 9913300.008 | 9874900.008 | Munaku project 12 months income statement (shs'000) Jan: 9836500.008; Munaku project 12 months income statement (shs'000) Feb: 9769900.008; Munaku project 12 months income statement (shs'000) Mar: 9752500.008; Munaku project 12 months income statement (shs'000) April: 49147100.04
Net profit |  | 886699.992 | 925099.992 | Munaku project 12 months income statement (shs'000) Jan: 963499.992; Munaku project 12 months income statement (shs'000) Feb: 1030099.992; Munaku project 12 months income statement (shs'000) Mar: 1047499.992; Munaku project 12 months income statement (shs'000) April: 4852899.96
Provision for taxation 30% |  | 266009.9976 | 277529.9976 | Munaku project 12 months income statement (shs'000) Jan: 289049.9976; Munaku project 12 months income statement (shs'000) Feb: 309029.9976; Munaku project 12 months income statement (shs'000) Mar: 314249.9976; Munaku project 12 months income statement (shs'000) April: 1455869.988
Profit after Taxation |  | 620689.9944 | 647569.9944 | Munaku project 12 months income statement (shs'000) Jan: 674449.9944; Munaku project 12 months income statement (shs'000) Feb: 721069.9944; Munaku project 12 months income statement (shs'000) Mar: 733249.9944; Munaku project 12 months income statement (shs'000) April: 3397029.972
| Some performance indicators | Shs'000 |  | Munaku project 12 months income statement (shs'000) Jan: 4142.004
| Return on Investment (Equity)% | #REF!
| Gross revenue | 10800000
| Revenue per kms | 450000
| Cost per kms | 413054.167
| Direct cost per kms | 298500
| Overhead costs per kms | 114554.167
| Profit margin per kms(total cost)% | 8.9445
| Gross margin per kms(direct cost)% | 50.7538
| Output in kms | 24
| Material cost per kms | 192000
| Machine cost per kms | #REF!
| Labour cost per kms | 60000
| Labour productivity (revenue per labour cost) | 180
Note on B15: Author: Changes from 12m to 15m per month when all equipment is hired
Note on B16: Author: only buildings of 170m will be depreciated over 20 years.
Note on C59: Author: Will change to shs 360,000 when all equipment is hired
Note on C63: Author: To change to only shs. 8,500 when all equipment is hired
Note on C65: Author: Figures to change as computed above with new gearing structure
Note on D27: Author: Yellow colour means the content of those cells could be changed with assumptions
Note on E6: Author: To change to 488,025 when price limit is removed.
Note on E12: Author: The amount will change to 30,000 on the assumption that all equipment is hired
Note on E16: Author: Depreciation would change to only shs 708,333 if the other equipment were hired instead.
Note on E18: Author: Interest for old loan only, to change when new structure is introduced and computed below
Note on L31: Author: Figures Figures for the existing loan only

## Model cashflows (hidden)
Particulars |  |  |  | Munaku project 12 months cash flow statement (shs'000)
Cost item | Narrative |  |  | Jan | Feb | Mar | April | May | June | july | Aug | Sept | oct | Nov | Dec | Total
Kilometres done |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24
Kilometres billed |  |  |  | Munaku project 12 months cash flow statement (shs'000) Feb: 4; Munaku project 12 months cash flow statement (shs'000) April: 4; Munaku project 12 months cash flow statement (shs'000) June: 4; Munaku project 12 months cash flow statement (shs'000) Aug: 4; Munaku project 12 months cash flow statement (shs'000) oct: 4; Munaku project 12 months cash flow statement (shs'000) Dec: 4 | 24
Price per km |  |  |  | Munaku project 12 months cash flow statement (shs'000) Feb: 450000; Munaku project 12 months cash flow statement (shs'000) April: 450000; Munaku project 12 months cash flow statement (shs'000) June: 450000; Munaku project 12 months cash flow statement (shs'000) Aug: 450000; Munaku project 12 months cash flow statement (shs'000) oct: 450000; Munaku project 12 months cash flow statement (shs'000) Dec: 450000
Revenue receipts |  |  |  | Munaku project 12 months cash flow statement (shs'000) Jan: 0; Munaku project 12 months cash flow statement (shs'000) April: 1800000; Munaku project 12 months cash flow statement (shs'000) June: 1800000; Munaku project 12 months cash flow statement (shs'000) Aug: 1800000; Munaku project 12 months cash flow statement (shs'000) oct: 1800000; Munaku project 12 months cash flow statement (shs'000) Dec: 1800000 | 9000000
Share capital | [15 empty] | 0 | bar: Munaku project 12 months cash flow statement (shs'000) Jan
Loan Capital | [15 empty] | 0 | bar: Munaku project 12 months cash flow statement (shs'000) Jan
Total receipts |  |  |  | 0 | 0 | 0 | 1800000 | 0 | 1800000 | 0 | 1800000 | 0 | 1800000 | 0 | 1800000 | 9000000
Payments
Additional land 5 acres |  |  |  | Munaku project 12 months cash flow statement (shs'000) Jan: 0 | 0
Building and equipment |  |  |  | Munaku project 12 months cash flow statement (shs'000) Jan: 170000 | 170000
Startup capital |  |  |  | Munaku project 12 months cash flow statement (shs'000) Jan: #REF! | #REF!
Material | 8,000 tonnesx20000 plus vat at 20% |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Direct labour | 60m/kms |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Machine hire | 15m/kms |  |  | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 360000
Fuel | 9000ltsx3500 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Overheads | 100m/kms |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Management salaries | 15m/month |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Owners dividends/drawings | 10m/month |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Depreciation | 354,167per kms | [14 empty] | 0
Amortisation | 1,250,000 per kms for 3 years | [14 empty] | 0
Loan repayment and interest |  |  |  | 26900 | 26900 | 26900 | 26900 | 26900 | 26900 | 26900 | 26900 | 26900 | 26900 | 26900 | 26900 | 322800
Total payments |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Net cash |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Opening balance |  |  | -999000 | -999000 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | -999000
Closing balance |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
means could change
shs'000
|  |  | Loan amount | Munaku project 12 months cash flow statement (shs'000) Mar: 750000
|  |  | Repayment over 48 months- monthly instalment | Munaku project 12 months cash flow statement (shs'000) Mar: 16000
|  |  | Simple interest calculation | Munaku project 12 months cash flow statement (shs'000) Feb: Year; Munaku project 12 months cash flow statement (shs'000) Mar: Start; Munaku project 12 months cash flow statement (shs'000) April: Repayed; Munaku project 12 months cash flow statement (shs'000) May: End; Munaku project 12 months cash flow statement (shs'000) June: Interest/year per y; Munaku project 12 months cash flow statement (shs'000) july: Interest/month; Munaku project 12 months cash flow statement (shs'000) Aug: Installment/month
[5 empty] | y1 | 750000 | 192000 | 558000 | 130800 | 10900 | 26900
[5 empty] | y2 | 558000 | 192000 | 366000 | 92400 | 7700
[5 empty] | y3 | 366000 | 192000 | 174000 | 54000 | 4500
[5 empty] | y4 | 174000 | 174000 | 0 | 17400 | 1450
[5 empty] | y5 | 0 | 0 | 0 | 0 | 0
[7 empty] | 750000 |  | 294600 | 24550
1044600
Year | Narrative | one | Two | Munaku project 12 months cash flow statement (shs'000) Jan: Three; Munaku project 12 months cash flow statement (shs'000) Feb: Four; Munaku project 12 months cash flow statement (shs'000) Mar: Five; Munaku project 12 months cash flow statement (shs'000) April: Total
Road work done in Kms | 0 | 24 | 24 | Munaku project 12 months cash flow statement (shs'000) Jan: 24; Munaku project 12 months cash flow statement (shs'000) Feb: 24; Munaku project 12 months cash flow statement (shs'000) Mar: 24; Munaku project 12 months cash flow statement (shs'000) April: 120
Price per km |  | 450000 | 450000 | Munaku project 12 months cash flow statement (shs'000) Jan: 450000; Munaku project 12 months cash flow statement (shs'000) Feb: 450000; Munaku project 12 months cash flow statement (shs'000) Mar: 450000
Revenue receipts |  | 9000000 | 10800000 | Munaku project 12 months cash flow statement (shs'000) Jan: 10800000; Munaku project 12 months cash flow statement (shs'000) Feb: 10800000; Munaku project 12 months cash flow statement (shs'000) Mar: 10800000; Munaku project 12 months cash flow statement (shs'000) April: 52200000
Share capital |  | 0 |  | Munaku project 12 months cash flow statement (shs'000) April: 0
Loan Capital |  | 0 |  | Munaku project 12 months cash flow statement (shs'000) April: 0
Total receipts |  | 9000000 | 10800000 | Munaku project 12 months cash flow statement (shs'000) Jan: 10800000; Munaku project 12 months cash flow statement (shs'000) Feb: 10800000; Munaku project 12 months cash flow statement (shs'000) Mar: 10800000; Munaku project 12 months cash flow statement (shs'000) April: 52200000; Munaku project 12 months cash flow statement (shs'000) May: 52200000
Payments
Additional land 5 acres |  | 0 |  | Munaku project 12 months cash flow statement (shs'000) April: 0
Building and equipment |  | 170000 |  | Munaku project 12 months cash flow statement (shs'000) April: 170000
Startup capital |  | #REF! |  | Munaku project 12 months cash flow statement (shs'000) April: #REF!
Material | 8,000 tonnesx20000 plus vat at 20% | #REF! | #REF! | Munaku project 12 months cash flow statement (shs'000) Jan: #REF!; Munaku project 12 months cash flow statement (shs'000) Feb: #REF!; Munaku project 12 months cash flow statement (shs'000) Mar: #REF!; Munaku project 12 months cash flow statement (shs'000) April: #REF!
Direct labour | 60m/kms | #REF! | #REF! | Munaku project 12 months cash flow statement (shs'000) Jan: #REF!; Munaku project 12 months cash flow statement (shs'000) Feb: #REF!; Munaku project 12 months cash flow statement (shs'000) Mar: #REF!; Munaku project 12 months cash flow statement (shs'000) April: #REF!
Machine hire | 12m/kms | 360000 | 360000 | Munaku project 12 months cash flow statement (shs'000) Jan: 360000; Munaku project 12 months cash flow statement (shs'000) Feb: 360000; Munaku project 12 months cash flow statement (shs'000) Mar: 360000; Munaku project 12 months cash flow statement (shs'000) April: 1800000
Fuel | 9000ltsx3500 | #REF! | #REF! | Munaku project 12 months cash flow statement (shs'000) Jan: #REF!; Munaku project 12 months cash flow statement (shs'000) Feb: #REF!; Munaku project 12 months cash flow statement (shs'000) Mar: #REF!; Munaku project 12 months cash flow statement (shs'000) April: #REF!
Overheads | 100m/kms | #REF! | #REF! | Munaku project 12 months cash flow statement (shs'000) Jan: #REF!; Munaku project 12 months cash flow statement (shs'000) Feb: #REF!; Munaku project 12 months cash flow statement (shs'000) Mar: #REF!; Munaku project 12 months cash flow statement (shs'000) April: #REF!
Management salaries | 15m/month | #REF! | #REF! | Munaku project 12 months cash flow statement (shs'000) Jan: #REF!; Munaku project 12 months cash flow statement (shs'000) Feb: #REF!; Munaku project 12 months cash flow statement (shs'000) Mar: #REF!; Munaku project 12 months cash flow statement (shs'000) April: #REF!
Owners dividends/drawings | 10m/month | 0 | 0 | Munaku project 12 months cash flow statement (shs'000) Jan: 0; Munaku project 12 months cash flow statement (shs'000) Feb: 0; Munaku project 12 months cash flow statement (shs'000) Mar: 0; Munaku project 12 months cash flow statement (shs'000) April: 0
Depreciation | 2,437,500 per kms | 0 | 0 | Munaku project 12 months cash flow statement (shs'000) Jan: 0; Munaku project 12 months cash flow statement (shs'000) Feb: 0; Munaku project 12 months cash flow statement (shs'000) Mar: 0; Munaku project 12 months cash flow statement (shs'000) April: 0
Amortisation | 1,250,000 per kms for 3 years | 0 | 0 | Munaku project 12 months cash flow statement (shs'000) Jan: 0; Munaku project 12 months cash flow statement (shs'000) Feb: 0; Munaku project 12 months cash flow statement (shs'000) Mar: 0; Munaku project 12 months cash flow statement (shs'000) April: 0
Loan repayment(including interest) |  | 322800 | 284400 | Munaku project 12 months cash flow statement (shs'000) Jan: 246000; Munaku project 12 months cash flow statement (shs'000) Feb: 191400; Munaku project 12 months cash flow statement (shs'000) Mar: 0; Munaku project 12 months cash flow statement (shs'000) April: 1044600
Taxation |  | 0 | 266009.9976 | Munaku project 12 months cash flow statement (shs'000) Jan: 277529.9976; Munaku project 12 months cash flow statement (shs'000) Feb: 289049.9976; Munaku project 12 months cash flow statement (shs'000) Mar: 309029.9976; Munaku project 12 months cash flow statement (shs'000) April: 1141619.9904
Total payments |  | #REF! | #REF! | Munaku project 12 months cash flow statement (shs'000) Jan: #REF!; Munaku project 12 months cash flow statement (shs'000) Feb: #REF!; Munaku project 12 months cash flow statement (shs'000) Mar: #REF!; Munaku project 12 months cash flow statement (shs'000) April: #REF!; Munaku project 12 months cash flow statement (shs'000) May: #REF!
0
Net cash |  | #REF! | #REF! | Munaku project 12 months cash flow statement (shs'000) Jan: #REF!; Munaku project 12 months cash flow statement (shs'000) Feb: #REF!; Munaku project 12 months cash flow statement (shs'000) Mar: #REF!; Munaku project 12 months cash flow statement (shs'000) April: #REF!; Munaku project 12 months cash flow statement (shs'000) May: #REF!
Opening balance | -999000 | -999000 | #REF! | Munaku project 12 months cash flow statement (shs'000) Jan: #REF!; Munaku project 12 months cash flow statement (shs'000) Feb: #REF!; Munaku project 12 months cash flow statement (shs'000) Mar: #REF!; Munaku project 12 months cash flow statement (shs'000) April: -999000
Closing balance |  | #REF! | #REF! | Munaku project 12 months cash flow statement (shs'000) Jan: #REF!; Munaku project 12 months cash flow statement (shs'000) Feb: #REF!; Munaku project 12 months cash flow statement (shs'000) Mar: #REF!; Munaku project 12 months cash flow statement (shs'000) April: #REF!; Munaku project 12 months cash flow statement (shs'000) May: #REF!
What if?
Note on E8: Author: These will be filled in with the equity and debt figures suggested to fund the business.
Note on E12: Author: The figures will change when the suggestion to leave out land purchase is adopted
Note on E13: Author: The figure will become shs 170m when the suggestion to hire equipment is adopted.
Note on E17: Author: The figure will change to shs. 30,000 when all equipment is to be hired instead.
Note on E21: Author: Figure to reduce to 0 when dividends are droped in the first year.
Note on E24: Author: Repayment figure Applies only to the existing loan of shs 7500m.
Note on F6: Author: Changes to 488,025 when price limit is removed.
Note on H7: Author: shifts to next month when credit period increases to 2 months.
Note on I77: Author: See how the cashflow figures differ with pprofit figures
Note on K35: Author: Figures Figures for the existing loan only
Note on Q7: Author: Total changes to 7,200,000 when credit is increased to 2 months.

## 10 km actual (hidden)
Actual 10 kms
Element |  | Description |  |  | Actual | Budgeted | Total | Usage | Price | Volume | Total
Materials | 90,000kms @ 22,000 | 8000tonnesx20000 plus vat at 20% | 192000000 |  | 1980000000 | 2304000000 | 324000000 | -240000000 | 180000000 | 384000000 | 324000000
Direct labour | 620m | 60m/kms | 60000000 |  | 620000000 | 720000000 | 100000000 |  | -20000000 | 120000000 | 100000000
Machine hire | 130m | 12m/kms | 12000000 |  | 130000000 | 144000000 | 14000000 |  |  |  | 0
Fuel | 100,000lts @3,200 | 9000ltsx3500 | 31500000 |  | 320000000 | 315000000 | -5000000 |  |  |  | 0
Overheads | 920m | 100m/kms | 100000000 |  | 920000000 | 1000000000 | 80000000 |  |  |  | 0
Management salaries | 150m | 15m/month | 7500000 |  | 150000000 | 75000000 | -75000000 |  |  |  | 0
Machine depreciation | 17.5m | 350m/7years/24 | 2083333.3333 |  | 17500000 | 20833333.3333 | 3333333.3333 |  |  |  | 0
Building depreciation | 4.25m | 170m/20 years/24 | 354166.6667 |  | 4250000 | 3541666.6667 | -708333.3333 |  |  |  | 0
Start up cost amortisation | 6.25m | 15mx6 months/3years/24 | 1250000 |  | 6250000 | 12500000 | 6250000 |  |  |  | 0
Total cost per kms |  |  | 406687500 |  | 4148000000 | 4594875000 | 446875000 | 446875000
Margin 20% |  |  | 81337500 |  | 4600000000 | 4500000000 | 100000000
Price | 4600m |  | 488025000 | Profits | 452000000 | -94875000 | -546875000 | 546875000
Acceptable market price |  | 4250000 | 450000000
Note on E14: Author: Since price is limited to shs 450m, the margin of 20% or 30% cannot be attained.

## M3 S2 DATA& SOLUTION
GROUP ACTIVITY
ACTUAL DATA FOR 6KM
Materials: 14,000 tones @ 22,000
Machine hours: 1500hrs @ 180,000/=
Fuel: 140,000 litres used @ 2,800/=
Labour:3,000mandays @9,000
BUDGET DATA FOR 6KM OF ROAD
Materials:15,000 tonnes @ 20,000
Machine hire: 1,200hrs @ 200,000
fuel 120,000 litres @3,000
labour:2,700mandays@10,000
Supervisor salary:3,000,000
Work will be billed on completion of every two kilometres and payments done in 30days
MUNAKU THREE MONTHS REVENUE BUDGET FOR 6 KM OF ROAD
PARTICULARS |  | KM | JAN | FEB | MAR | Total
NUMBER OF KM |  | 1 | 2 | 2 | 2
|  |  | Ugx 000 | Ugx 000 | Ugx 000 | Ugx 000
Revenue from contract | 404300 | 202150 | 403000 | 403000 | 403000 | 1209000
Other incomes |  |  | 0 | 0 | 0 | 0
Total Income |  |  | 403000 | 403000 | 403000 | 1209000
Projected Expenditure | [5 empty] | 0
Materials | 5000 tonnes @ 20,000 | 2500 | 100000 | 100000 | 100000 | 300000
Machine hire | 400 Hrs @ 200,000 | 200 | 80000 | 80000 | 80000 | 240000
Fuel | 100 litres/hr @ 3,000 | 20000 | 120000 | 120000 | 120000 | 360000
Labour | 900 man days @ 10000 | 450 | 9000 | 9000 | 9000 | 27000
Supervisors salary | 2 persons @ 500,000 per month | 500 | 1000 | 1000 | 1000 | 3000
Total Expenditure |  |  | 310000 | 310000 | 310000 | 930000
Surplus/(deficit) |  |  | 93000 | 93000 | 93000 | 279000
MUNAKU THREE MONTHS CASH BUDGET FOR 6 KM OF ROAD
PARTICULARS |  |  | JAN | FEB | MAR | Total
NUMBER OF KM |  |  | 2 | 2 | 2
|  |  | Ugx 000 | Ugx 000 | Ugx 000 | Ugx 000
Receipts: |  |  | 0 |  |  | 0
From contract (30 days credit) |  |  |  | 403000 | 403000 | 806000
From other sources |  |  | 0 | 0 | 0 | 0
Total Receipts |  |  | 0 | 403000 | 403000 | 806000
0
Payments | [5 empty] | 0
Materials | 5000 tonnes @ 20,000 |  | 100000 | 100000 | 100000 | 300000
Machine hire | 400 Hrs @ 200,000 |  | 80000 | 80000 | 80000 | 240000
Fuel | 100 litres/hr @ 3,000 |  | 120000 | 120000 | 120000 | 360000
Labour | 900 man days @ 10000 |  | 9000 | 9000 | 9000 | 27000
Supervisors salary | 2 persons @ 500,000 per month |  | 1000 | 1000 | 1000 | 3000
Total Payments |  |  | 310000 | 310000 | 310000 | 930000
Net Cash change |  |  | -310000 | 93000 | 93000 | -124000
Opening balance |  |  | 0 | -310000 | -217000 | -527000
Closing balance |  |  | -310000 | -217000 | -124000 | -651000

## M3 S3 CONTROL BUDGET
SIMPLE CONTROL BUDGET FOR 1KM OF GRAVEL ROAD
ITEM |  | QUANTITY | UNIT COST | AMOUNT
Materials: Gravel | 5000tones/2 | 2500 | 20000 | 50000000
Direct Labour | 900 man days/2 | 450 | 10000 | 4500000
Machine Hire | 400hours/2 | 200 | 200000 | 40000000
machine Fuel | 400*100/2 | 20000 | 3000 | 60000000
Supervision | 1 month | 2 | 500000 | 1000000
Total Cost |  |  |  | 155500000
Margin |  | 30% |  | 46650000
BID PRICE |  |  |  | 202150000
BUDGET FOR 5KM ROAD DONE IN 3MONTHS
ITEM |  | QUANTITY | UNIT COST | UNIT COST/KM | 5KM
Materials: Gravel | 5000tones/2 | 2500 | 20000 | 50000000 | 5 | 250000000
Direct Labour | 900hours/2 | 450 | 10000 | 4500000 | 5 | 22500000
Machine Hire | 400hours/2 | 200 | 200000 | 40000000 | 5 | 200000000
Machine Fuel | 400*100/2 | 20000 | 3000 | 60000000 | 5 | 300000000
Supervision | 1 month | 2 | 500000 | 1000000 | 3 | 3000000
Total Cost |  |  |  | 155500000 |  | 775500000
Margin |  | 30% |  | 46650000 |  | 232650000
BID PRICE |  |  |  | 202150000 |  | 1008150000
Note on F20: Author: supervision will be for 3month for 5km work since 1.5kms are done per month

## M3 S3 VARIANCES
TOTAL COST VARIANCES
ANALYSIS
ITEM | BUDGET FOR 3MONTH | ACTUAL FOR 3MONTH | VARIANCE | COMMENTS |  | Budget | Actual | Variance |  | AMOUNT
Material cost | 300000000 | 308000000 | -8000000 | Adverse | Material Price | 20000 | 22000 | -2000 | 14000 | -28000000
|  |  | 0 |  | Material Usuage-Tones | 15000 | 14000 | 1000 | 20000 | 20000000
Labour | 27000000 | 27000000 | 0 |  | Labour Rate | 10000 | 9000 | 1000 | 3000 | 3000000
|  |  | 0 |  | Labour Efficiency in Hours | 2700 | 3000 | -300 | 10000 | -3000000
Machine | 240000000 | 270000000 | -30000000 | Adverse | Machine Rate | 200000 | 180000 | 20000 | 1500 | 30000000
|  |  | 0 |  | Machine Efficiency | 1200 | 1500 | -300 | 200000 | -60000000
Fuel | 360000000 | 392000000 | -32000000 | Adverse | Fuel Price | 3000 | 2800 | 200 | 140000 | 28000000
Administration(supervision) | 3000000 | 3000000 | 0 |  | Fuel usuage | 150000 | 140000 | 10000 | 3000 | 30000000
TOTAL COST | 930000000 | 1000000000 | -70000000 | Adverse | Fuel Effieciency(based on machine hours) | 120000 | 150000 | -30000 | 3000 | -90000000
REVENUE | 1209000000 | 1209000000 | [7 empty] | -70000000
PROFIT | 279000000 | 209000000 | 70000000
VARIANCE | PERSON RESPONSIBLE | Posible Causes
Material cost/price | Purchaser | wrong price estimates, use of different quality of materials,inflation,rush purchase,change in quantity of materials
Labour Rate | Supervisor | Use of different Grade of Labour, change in basic wage rate, unplanned overtime.
Fuel Price | Machine Operator, Purchaser | Change in fuel prices, Change in quantity of fuel used
Note on G13: 0onyu: amount of fuel that shd hv bn used based on buget 100ltrs per hr-1500hrs of machine